## Read Me
Following the circular on Ex-Gratia Co-Sharing of Prolongation Costs in public sector projects due to COVID-19 dated 29 June 2020, this template is jointly developed with SCAL and government agencies to facilitate the claim process. Main contractors can adopt and modify the template as necessary and are not restricted to this template. Government agencies are reminded that claims for prolongation costs cannot be rejected on the ground that a different format is used. For subcontractors involved in public sector projects, they can provide their claims to their main contractors. Main contractors would incorporate subcontractors’ claims into the claims to be submitted to government agencies. We encourage main contractors involved in public sector projects to put in their claims for prolongation costs using the template provided. In situation in which the Extension of Time (EOT) is still not ascertained, main contractors can submit the claims based on the EOT they are requesting or intend to request to expedite the process.
Note: This template is updated to align with the adjustments made to the earlier circular. Pls refer to Circular on Treatment of Claims Arising from COVID-19 in Public Sector Construction Contracts (dated 25 Sep 2020) for details.

## Cost Template
Claim template for prolongation costs due to COVID-19
| Contract sum | 200000000
| Co-sharing is capped at 0.2% per month | 400000 | per month cap
| Overall capped at 1.8% of contract sum (9 months) | 3600000 | overall cap
| EOT granted due to COVID-19 (to-date) | X | months | Refer to Row 9
| Breakdown of expenses incurred^ | costs per month ($)
| EOT (Month) | 1 | 2 | X | (New Columns to be added as necessary)
A | Plant and equipment costs | 400000 | 400000 | 0
| Main Contractor | (example) | (example)
1 | Rental cost (Any items used in project that require contractor to pay rental. Include but not limited to steel plate, formworks, piling rig, crane, working platform etc.) | 50000 | 50000
2 | Owned-equipment costs (e.g. machine depreciation) | 50000 | 50000
3 | Running cost of plant/equipment (e.g. diesel if in use) | 50000 | 50000
4 | Maintenance cost (e.g. spare parts and repair) | 50000 | 50000
Subcontractor / Suppliers
5 | Rental cost (Any items used in project that require contractor to pay rental. Include but not limited to steel plate, formworks, piling rig, crane, working platform etc.) | 50000 | 50000
6 | Owned-equipment costs (e.g. machine depreciation) | 50000 | 50000
7 | Running cost of plant/equipment (e.g. diesel if in use) | 50000 | 50000
8 | Maintenance cost (e.g. spare parts and repair) | 50000 | 50000
B | Site maintenance costs | 500000 | 500000 | 0
Main Contractor
1 | Vector and pest control | 50000 | 50000
2 | Site security | 50000 | 50000
3 | Utilities (e.g. utilities bills) | 50000 | 50000
4 | Housekeeping | 50000 | 50000
5 | Works carried out to prepare for CB (temporary works done to ensure the safety of site i.e. additional supports, back filling, lean concrete etc ) | 50000 | 50000
Subcontractor / Suppliers
6 | Vector and pest control | 50000 | 50000
7 | Site security | 50000 | 50000
8 | Utilities (e.g. utilities bills) | 50000 | 50000
9 | Housekeeping | 50000 | 50000
10 | Works carried out to prepare for CB (temporary works done to ensure the safety of site i.e. additional supports, back filling, lean concrete etc ) | 50000 | 50000
C | Other Preliminaries | 300000 | 300000
Main Contractor
1 | Extension of project insurance | 50000 | 50000
2 | Extension of performance bonds | 50000 | 50000
3 | Storage costs (for materials, equipment and fitting out works) | 50000 | 50000
4 | Site Office rental (after deducting other govt rental rebates)
5 | Temporary Occupation Licence (TOL) land rental
Subcontractor / Suppliers
6 | Extension of project insurance | 50000 | 50000
7 | Extension of performance bonds | 50000 | 50000
8 | Storage costs (for materials, equipment and fitting out works) | 50000 | 50000
9 | Site Office rental (after deducting other govt rental rebates)
10 | Temporary Occupation Licence (TOL) land rental
| Total expenses incurred per month (A+B+C) | 1200000 | 1200000 | 0
| 50% of prolongation costs | 600000 | 600000 | 0
| Co-sharing amount per month (capped at 0.2%) | 400000 | 400000 | 0
| Cummulated amount of co-sharing | 800000
Notes:
xxx | Fills to be completed by contractors
^ | Based on actual costs incurred. GST is not applicable to ex-gratia payment and excluded from the co-payment
# | Columns to be added as necessary.