## Eligibility
Eligibility check - Claim for co-sharing of qualifying costs in construction contracts under Part 8B of COVID-19 (Temporary Measures) Act 2020 ("Act")
Inputs in blue fonts below are examples of inputs for illustration only
Act ref | Requirement under the Act |  | Information required from the Party who submits the claim | Self check by the Party who submits the claim (please provide input below) | Eligible for relief under Part 8B (Yes/No)
Eligibility for relief under Part 8B
Sect 39C | Contract falls under definition of construction contract under section 2 of the Building & Construction Industry Security of Payment Act |  | Description of contract/works | Addition & alternation works for a 4-storey industrial building | <For input>
Sect 39C (a) | Contract was entered into before | 2020-03-25 | Date of Letter of Award/Agreement | 2020-02-24 | Yes
Sect 39C (b) | Contract remains in force on | 2020-11-02 | Final Contract completion date | 2021-01-31 | Yes
Sect 39C (c) | Party A (i.e. the party which receives the claim) is not an individual |  | Name of Client | XYZ developer Pte Ltd | <For input>
Sect 39C (d) | There were construction works that were not certified to be completed under the construction contracts as at 7 April 2020 |  | Description of outstanding works | Aluminium and glazing works for Level 7 to roof | <For input>
All criteria set out above must be met (i.e. all "Yes") to be eligible for the co-sharing
Disclaimer: The purpose of this template is to facilitate parties to submit and assess claims under Part 8B of the COVID-19 (Temporary Measures) Act. While every effort has been made to ensure the accuracy of this template, the Building and Construction Authority (BCA) will not be liable for any loss arising from use of this template.

## Qualifying costs
TEMPLATE - Claim for co-sharing of qualifying costs in construction contracts under Part 8B of COVID-19 (Temporary Measures) Act 2020 ("Act")
Disclaimer: The purpose of this template is to facilitate parties to submit and assess claims under Part 8B of the COVID-19 (Temporary Measures) Act. While every effort has been made to ensure the accuracy of this template, the Building and Construction Authority (BCA) will not be liable for any loss arising from use of this template.
Inputs in blue fonts below are examples of inputs for illustration only. Users are free to amend/adjust based on their claims.
Act ref Requirement under the Act | Project Info | Specified period 1 7 Apr 2020 to 30 Apr 2020 | Specified period 2 1 May 2020 to 31 May 2020 | Specified period 3 1 Jun 2020 to 30 Jun 2020 | Specified period 4 1 Jul 2020 to 31 Jul 2020 | Specified period 5 1 Aug 2020 to 31 Aug 2020 | Specified period 6 1 Sep 2020 to 30 Sep 2020 | Specified period 7 1 Oct 2020 to 31 Oct 2020 | Specified period 8 1 Nov 2020 to 30 Nov 2020 | Specified period 9 1 Dec 2020 to 31 Dec 2020 | Specified period 10 1 Jan 2021 to 31 Jan 2021 | Specified period 11 1 Feb 2021 to 28 Feb 2021 | Specified period 12 1 Mar 2021 to 31 Mar 2021 | Specified period 13 1 Apr 2021 to 30 Apr 2021 | Specified period 14 1 May 2021 to 31 May 2021 | Specified period 15 1 Jun 2021 to 30 Jun 2021 | Specified period 16 1 Jul 2021 to 31 Jul 2021 | Specified period 17 1 Aug 2021 to 31 Aug 2021 | Specified period 18 1 Sep 2021 to 30 Sep 2021 | Specified period 19 1 Oct 2021 to 31 Oct 2021 | Specified period 20 1 Nov 2021 to 30 Nov 2021 | Specified period 21 1 Dec 2021 to 31 Dec 2021 | Specified period 20 1 Jan 2022 to 31 Jan 2022 | Specified period 21 1 Feb 2022 to 28 Feb 2022
Unable to complete construction works by original completion date
Sect 39D(1)(a) Party B is unable to complete construction works by completion date (the completion date refers to original completion date before applying the extension granted under Part 8A) | Input on eligbility ("Latest estimated completion date" has to be later than "Original contract completion date" | Eligible
| Original contract completion date | 2022-05-15
| Latest estimated completion date | 2022-09-30
Qualifying Costs
Sect 39D(1)(b) B’s inability is to a material extent caused by a COVID-19 event | Start date of the period in which B's inability to complete construction works by the completion date is to a material extent caused by a COVID-19 event | 2020-04-07 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | [contractor to input accordingly]
| End date of the period in which B's inability to complete construction works by the completion date is to a material extent caused by a COVID-19 event | 2020-04-30 | 2020-05-31 | 2020-06-30 | 2020-07-31 | 2020-08-15 | 2020-09-07 | [contractor to input accordingly]
| Brief description to substantiate that the inability is to a material extent caused by a COVID-19 event | - Suspension of activities at workplaces due to COVID-19 from 7 Apr until the date when all dormitories are announced to be cleared on 6 Aug 2020 (122 days) - Works only started with sufficient workers on site for structural works from 16 Aug 2020 onwards |  |  |  |  | 50% of workers for glazing works on SHN for 14 days, requiring extra 7 days (from 1 Sep 2020 to 7 Sep 2020, both days inclusive) to complete the glazing works from level 7 to roof. As seen in the revised programme, the watertightness of the building is on critical path. | [contractor to input accordingly]
| Substantiating documents can be attached as Appendix with this claim | - | - | Refer to BCA approval obtained in Appendix xx | Refer to revised programme and critical path analysis in Appendix x.
| SO/Architect/Client's assessment on start and end date of the period in which B's inability to complete construction works by the completion date is to a material extent caused by a COVID-19 event | Contractor has demonstrated inability to complete construction works for the specified period from 7 Apr 2020 to 2 Jun 2020 to a material extent caused by a COVID-19 event
Sect 39D(1) (3) qualifying costs must be pro-rated for each of those specified periods | Qualifying cost incurred within the specified period indicated in rows 10 and 11 needs to be pro-rated | From 07-Apr-2020 to 30-Apr-2020 | From 01-May-2020 to 31-May-2020 | From 01-Jun-2020 to 30-Jun-2020 | From 01-Jul-2020 to 31-Jul-2020 | From 01-Aug-2020 to 15-Aug-2020 | From 01-Sep-2020 to 07-Sep-2020 | [contractor to input accordingly]
Sect 39D (9) (a) rent or hire-purchase instalment for any plant or equipment required | Rental cost (Any items used in project that require contractor to pay rental. Include but not limited to steel plate, formworks, piling rig, crane, working platform etc.) | 5000 | 50000 | 50000 | 50000 | 25000 | 11666.6667 | [contractor to input accordingly]
| Running cost of plant/equipment (e.g. diesel if in use) |  | 50000 | 50000 | 50000 | 25000 | 11666.6667 | [contractor to input accordingly]
| Maintenance cost (e.g. spare parts and repair) |  | 50000 | 50000 | 50000 | 25000 | 11666.6667 | [contractor to input accordingly]
| Cost payable to subcontractors | [6 empty] | [contractor to input accordingly]
| Contractor can add on as necessary | [6 empty] | [contractor to input accordingly]
Sect 39D (9) (b) costs for maintaining the construction site | Vector and pest control | 5000 | 50000 | 50000 | 50000 | 25000 | 11666.6667 | [contractor to input accordingly]
| Site security |  | 50000 | 50000 | 50000 | 25000 | 11666.6667 | [contractor to input accordingly]
| Utilities (e.g. utilities bills) |  | 50000 | 50000 | 50000 | 25000 | 11666.6667 | [contractor to input accordingly]
| Housekeeping |  | 50000 | 50000 | 50000 | 25000 | 11666.6667 | [contractor to input accordingly]
| Works carried out to prepare for CB (temporary works done to ensure the safety of site i.e. additional supports, back filling, lean concrete etc ) |  | 50000 | 50000 | 50000 | 25000 | 11666.6667 | [contractor to input accordingly]
| Site Office rental (after deducting other govt rental rebates) |  | 50000 | 50000 | 50000 | 25000 | 11666.6667 | [contractor to input accordingly]
| Cost payable to subcontractors | [6 empty] | [contractor to input accordingly]
| Contractor can add on as necessary | [6 empty] | [contractor to input accordingly]
Sect 39D (9) (c) costs to extend the validity period of any insurance obtained and any performance bond | Extension of project insurance | 5000 | 50000 | 50000 | 50000 | 25000 | 11666.6667 | [contractor to input accordingly]
| Extension of performance bonds | 5000 | 50000 | 50000 | 50000 | 25000 | 11666.6667 | [contractor to input accordingly]
| Cost payable to subcontractors | [6 empty] | [contractor to input accordingly]
Sect 39D (9) (d) rent or other fee for the use of premises in Singapore to store any materials or equipment | Storage costs in Singapore (for materials, equipment and fitting out works) | 5000 | 50000 | 50000 | 50000 | 25000 | 11666.6667 | [contractor to input accordingly]
| Temporary Occupation Licence (TOL) land rental (after deducting other govt rental rebates) |  | 50000 | 50000 | 50000 | 25000 | 11666.6667 | [contractor to input accordingly]
| Cost payable to subcontractors | [6 empty] | [contractor to input accordingly]
Sect 39D (1) the lesser of the following amounts for each specified period (d) 50% of the total qualifying costs for anything done for or provided to or enjoyed by B in the specified period; (e) 0.2% of the contract sum. | Total qualifying costs | 25000 | 650000 | 650000 | 650000 | 325000 | 151666.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 50% of the total qualifying costs | 12500 | 325000 | 325000 | 325000 | 162500 | 75833.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Contract sum | 100000000 | 100000000 | 100000000 | 100000000 | 100000000 | 100000000 | 100000000 | 100000000 | 100000000 | 100000000 | 100000000 | 100000000 | 100000000 | 100000000 | 100000000 | 100000000 | 100000000 | 100000000 | 100000000 | 100000000 | 100000000 | 100000000 | 100000000
| 0.2% of the contract sum | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000
| Qualifying costs for each specified period | 12500 | 200000 | 200000 | 200000 | 162500 | 75833.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Qualifying costs | 850833.3333
Sect 39D (2) The total amount that B may claim under subsection (1) must not exceed 1.8% of the contract sum | 1.8% of the contract sum | 1800000
| Total qualifying costs that B is entitled to | 850833.3333